## Sheet1
task | start date | end date | duration
Preliminary Investigation | 2021-07-04 | 2021-07-07 | 3
Project Topic Discussion | 2021-07-10 | 2021-07-16 | 6
Current System Description | 2021-07-17 | 2021-07-18 | 1
Proposed System Description | 2021-07-19 | 2021-07-20 | 1
Feasibility Study | 2021-07-21 | 2021-07-22 | 1
| 44381 | 44399
Formulas:
duration = DATEDIF([start date],[end date],"D")